## Projects 2019-2020
Proposal Date | Category | Item | Status | Work Lead | Others Involved | Deliverable | Next Steps | Delivery Date | Issues/Questions
Carry-over |  | Virtual meetings for ULMS Systems group?? | Complete
Carry-over |  | ULMS Systems: Bursar fines and fees | Active | David Walker | Jonathan Smith, Erik Beck | Create comprehensive documentation on what different campuses are doing for fine payment & record integration with Alma user accounts. | 10/19: Review information on the Fines and Fees Integration page in the ULMS confluence site and identify updates to that documentation.
Carry-over |  | ULMS Systems: ILLiad integration | Active | David Walker |  | Document who has successfully implemented Illiad-Alma integrations. | 10/19: Send an inquiry to campuses to see who has implemented any Illiad-Alma integrations.
Carry-over |  | Collect historical STIM documents and make available on Confluence (in new STIM space) | Active | Ron Rodriguez |  | Archive historical STIM documents in one shared system, Confluence. | 9/19: Submit historical documents to Aegan1@csustan.edu
2019-08-07 |  | Survey of vendor relationships in CSU libraries | Active | Christina Mune Christina Hennessey | Heather Cribbs | Create documentation of shared resources regarding vendor relationships | 10/19: Christina and Heather will provide a real plan
2019-08-07 |  | Study of group study rooms in the CSU libraries | Active | Christina Hennessey Kevin Jeffrey | Heather Cribbs Renaldo Gjoshe | Create documentation of shared resources regarding: Reservation system, budget, latest AV | Contact Fullerton IT Dept at atl@fullerton.edu
2019-08-07 |  | Makerspace Policies | Active | Mike DeMars, Jonathan Smith | Gabriel Gardner Ron Rodriguez | Create documentation of various Makerspace policies | Research Long Beach Public Library at: http://www.longbeach.gov/library/visit/studios/
2019-08-07 |  | Survey of digitization labs in the CSU libraries | Active | Erik Beck | Heather Cribbs | Create documentation of shared services, pricing and best practices | Create survey
2019-08-07 |  | Survey of faculty profile software | Scholcomm | Heather Cribbs
2019-10-10 |  | Carpentries and the Potential for being a Member Organization | Active | David Walker | Christina Mune | Learn more about membership with Carpentries | Christina Mune and David Walker will research further and provide an update.

## Projects 2017-2019
Priority | Category | Item | Status | Work Lead | Others Involved | Deliverable | Next Steps | Delivery Date | Issues/Questions
Low | STIM | Virtual meetings for ULMS Systems group?? | STIM will serve in this capacity | ?? | ?? | ?? | ?? | ??
| Complete | Handle dilemma (replaced by DOI/PURL?) in the IR (and beyond); include datasets | Active | Andrew Weiss | Jeremy Shellhase, David Walker, Katie Lage | Report that compares DOI/Handle/ARK as well as scalable solutions for CSU-wide DOI minting: i.e. DataCite, EZID, Crossref for review at April meeting | Report draft in progress | March-April 2018 | 1) Is it worthwhile to adopt a system-wide DOI / or other persistent ID service for all campuses? 2) costs? 3) positive impact on adoption? 4) negatives?
| Complete | VIVO | Active | Bin Zhang |  | Initial installation and configuration underway
| Complete | Keeping the momentum going with working groups | COMPLETE | Kevin Cloud | Zach Vowell, Renaldo Gjoshe | Renaldo, Zach, and Carmen asked the people that lead the discussions at the 2017 meeting if they would be willing to lead the IGs for a 2 year term. | IG leaders would help plan the IR meeting in the summer.
| Complete | Tipasa pilot group for system? | ?? | David Walker | ISPIE to be consulted | ?? | David reaching out to OCLC for a webinar | ??
| Complete | Develop and support applications | ON HOLD | David Walker |  | ??
Medium | STIM | ULMS Systems group hangover item: Bursar fines and fees – Dave - Jonathan | Active | David Walker | Jonathan Smith | Email LIBIT on who's interested/willing to work on this for PayPal & CashNet integration
| ULMS | ULMS Systems group hangover item: Learning Management Integration | ON HOLD | David Walker
Medium | STIM | ULMS Systems group hangover item: ILLiad integration | ON HOLD | David Walker |  | ILLiad will be replaced with Tipasa; integrations with ULMS and other software will take place during the transition
| ScholComm | Journal publishing platform | Active | Jeremy Shellhase | Jonathan Smith, Carmen Mitchell | Report on different publishing platforms; |  | 2020-01-01
| Complete | SMS texting of call numbers | COMPLETE | David Walker |  | Add on to Bookfinder "locate" function added to GitHub | Moved on to ULMS workgroup?
| Complete | Makerspaces, COP/best practices (for libraries) leadership | Active | Jonathan Smith | Jonathan to name | Formation of Community of Practice | Virtual meeting in Feb to organize, participation in CSU Maker Convening in June (at SSU) | 2018-06-01 | Identifying campus champions
| Digital Repositories | Adding 3d model viewer to IR - background research | ON HOLD | Jonathan Smith |  | tabled until migrations are completed.
| Complete | How to shepherd the next annual LIBIT meeting | Active | Jonathan Smith |  | Plan for 2018 LIBIT meeting | Waiting on feedback from COLD re: resources to support meetings and frequency |  | Frequency of meeting? Hold adjacent to other meetings? Host?
| ScholComm | LOCKSS / MetaArchive / Portico report comparing options | Active | Karen Schneider | Patrick Newell, Bin Zhang | Report comparing the three projects for post-cancellation access - for COLD to fund | Patrick to locate former LOCKSS reports; will share with Karen and Bin
| Complete | Data management plans / DMPtool - background research on partnership and institutional templates | COMPLETE | Katie Lage | Carmen Mitchell, Andrew Weiss | Posting to CSULIT
| Digital Repositories | Archives/Image and other collections into Samvera – technical planning | Active | Kevin Cloud |  | Technical plan (and budget if necessary) for completing software confirmation and miegration of data
| Digital Repositories | Video in Scholarworks – background research and technical planning | ON HOLD | Kevin Cloud |  | tabled until migrations are completed.
| Digital Repositories | Polling campuses to prioritize Scholarworks coding (and coding sprints) | Active | Kevin Cloud | Carmen Mitchell | Aim for coding spring at the IR meeting in Summer 2018. CM/KC to plan.
| Digital Repositories | Adding 3d model viewer to IR - technical planning | ON HOLD | Kevin Cloud |  | tabled until migrations are completed.
| Digital Repositories | Migrating CONTENTdm to Samvera | Active | Kevin Cloud | Renaldo |  | Fresno doing pilot; may have results to share in March
| Digital Repositories | Controlled vocabulary for IR | ON HOLD | ON HOLD | Lucy Liu
| Digital Repositories | Faculty profiles | ON HOLD | ON HOLD |  | On hold until Samvera migration complete
Low | STIM | Collect historical STIM documents and make available on Confluence (in new STIM space) | Active | Patrick Newell |  | Collected STIM documents from past years
| Digital Repositories | Guidelines for data sets in IR | Active | Renaldo Gjoshe | Lucy Liu (Fresno)/Katie Lage | Renaldo will share data dictionary at next STIM meeting (complete Dec 2017) | Discussion at January 2018 STIM meeting
| Digital Repositories | How will collections from ContentDM/Islandora fit into Samvera / Multiple collections in repository- background research | Active | Renaldo Gjoshe
| Complete | MALT (Maps and Aerial Locator Tool) adoption/use by CSU libraries | Active | Renaldo Gjoshe | Patrick Newell
| Digital Repositories | Archives/Image and other collections into Samvera – background research | Active | Zach Vowell | Kevin Cloud | Brief report on current state of Samvera capabilities for image viewing | Report review at May STIM meeting | 2017-05-01
| ScholComm | Centralized instance of ArchiveSpace | Active | Zach Vowell | Bin Zhang | Zach report on hosting options; Bin to gather info on interested campuses at CSUCM meeting; Eddie asked to find pricing for CSU |  | 2017-02-01
| Complete | ORCID / Identity management for repositories | Active | Zach Vowell | Katie Lage, Andrew Weiss | Will share report and bring to STIM for COLD review |  | DISCUSS AT JAN MTG