## Slide 1: Project Review & Post-Go Live Governance
ULMS Team
COLD Meeting, Channel Islands Sept 2016

## Slide 2: Overview
Project review & update
Governance post go-live

## Slide 3: Project review & update

## Slide 4: Timeline: Pre-Implementation
Campus Project Managers selected Governance structure formed
CO staff come onboard (Sarina and Mallory) Authentication & PeopleSoft work begun
Vanguard Group (Fresno, Northridge, San Jose) complete test load, functional training
Summer 2015
Fall 2015
Winter 2016

## Slide 5: Timeline: Implementation
Full project kick-off
Data from current ILS, ERM systems exported to Alma, Functional Calls begin
All campuses begin testing data in Alma Resource Sharing taskforce formed
In-person Ex Libris-led workshop at San Jose
March 2016
April 2016
Summer 2016
August 2016

## Slide 6: Timeline: From here to go-live
Focus on training, testing and final migration preparation
Check-in calls with PMs
Working Groups focused on policy decisions and making recommendations to COLD
Final migration phase begins
Go live!
Fall 2016- Spring 2017
April 2017
June 2017

## Slide 7: Training
Fall and Spring webinars planned
  ExLibris: covering material not covered in depth or at all in August
  CSU: task-based webinars on topics suggested by CSU personnel
January Workshop
  Ex Libris-delivered
  Goal is to focus on important consortium workflows
  Driven by Working Group policy decisions
Primo functional calls in October

## Slide 8: Training (cont’d)
Make sure to work with your PM and campus trainers and encourage them to start training your staff and faculty now!

## Slide 9: Testing
Data issues to be reported to Ex Libris by Dec 15
Functionality/Configuration issues to be reported by Mar 31
CO staff have developed guidelines for testing – available on Confluence

## Slide 10: Go-Live at a glance
Final migration work begins May 2017
  Technical Freeze: 4 weeks out from your Go-Live date
  Fulfillment Freeze: 48 hrs out from your Go-Live date
Go-Live dates in June 2017
  Week of June 13: Maritime, East Bay, Humboldt, Chico, Bakersfield, Dominguez Hills, Northridge, Fresno
  Week of June 20 Monterey Bay, Sonoma, Fullerton, Channel Islands, Los Angeles, Long Beach, Pomona
  Week of June 27 San Francisco, San Jose, Stanislaus, San Bernardino, San Luis Obispo, Moss Landing, San Diego
  Sacramento, San Marcos linked to NZ at end

## Slide 11: A few more words about Go-Live
All hands on deck from April to late-July/early-August
  Increased stress & workload on line staff & PMs (Be Kind)
  TS staff will be discouraged from working in ILS during technical freeze (what to do with free time?)
  Staff vacations will need to be managed during this time
    Will need PMs project knowledge on hand
    Key staff who export and evaluate data in current ILS and Alma/Primo
  Need as many eyeballs as possible to find issues during rest of summer
More specifics about timeline at later COLD meeting

## Slide 12: Questions on Project Update?

## Slide 13: ULMS Governance Post Go-Live

## Slide 14: Initial Questions
What level of involvement does COLD want?
How different is our mission and structure from other Alma consortia?
Current ULMS governance structure focused on inclusivity of staff/faculty – will need more nimble structure in production system

## Slide 15: What is the need for governance?
Ongoing policy & procedure development
Create best practice-based models of joint operations
Encourage collaboration
Identify areas for new efficiencies & services using Alma & Primo
Enabling the ULMS to achieve strategic direction
  The ULMS is a unified, shared library services platform that provides the critical infrastructure needed to support efficient management and delivery of print and electronic resources and collaborative collection development to enable equitable student success across the CSU.

## Slide 16: Current North America Alma Consortia
Orbis Cascade
U Wisconsin
In progress:
University System of Georgia
Montana
WRLG

## Slide 17: Let’s Look At Orbis
39 colleges and universities in Pacific Northwest
Small teams (5-7 members)
  Members serve 2 year terms
  Members do not represent their campus, as such
  Teams are in communication with campus reps
  Library Director on each team, chair appointed by Board
Ad hoc working groups

## Slide 18: Orbis SLIS Teams
Assessment – like CAT
Collaborative Workforce – shared workflows, training, documentation, and professional development
Content Creation & Dissemination – special collections, archives, and digital repositories.
Discovery & Delivery – Primo & resource sharing
Shared Content – Like EAR
Systems – Like STIM, but also Alma/Primo customer support.

## Slide 19: What about the University of Wisconsin System?
26 campuses, half community colleges.
Madison provides technical support and direction
Council of U of Wisc Libraries (CUWL) provides oversight
1 central position (bought-out from Madison), no central office

## Slide 20: U Wisc Structure
Steering Committee (5 voting members, Project Director, chairs of groups)
Campus contact - 1 per campus
Expertise Groups (5-7 members) – down from 8
  Discovery/Fulfillment
  Shared Content
  Technical/Data
Temporary structure - will evaluate structure after this year

## Slide 21: Back to the questions
What level of involvement does COLD want?
How different is our mission and structure from other Alma consortia?
Current ULMS governance structure focused on inclusivity of staff/faculty – will need more nimble structure in production system

## Slide 22: Potential CSU Directions
Oversight
  Empowered to approve low-level policy recommendations from teams
  Form ULMS Council
    CO and COLD liaison membership
  COLD subcommittee
    Chaired by COLD rep
    COLD process for nominating members
    CO representation

## Slide 23: Potential CSU Directions
Form teams
  Functional Areas (e.g: Fulfillment, Acquisitions)
  Centralized functions (e.g: Shared Cataloging, ERM, Resource Sharing)
  Specific topics (e.g.: Training, Marketing)
  Oversight Rep on each
  Teams work with campus reps on issues, policies and best practices
Consider Orbis approach of blending ULMS functional areas with existing COLD committees to best support COLD strategic initiatives?

## Slide 24: Thoughts?