## Sheet1
Space | Location | Notes | Status
Ex Com Meeting Room | LIB 5006 | Served continental breakfast of store-bought items and in-library made coffee. | P
Lunch Space | LIB 2022 | Caterer scheduled to arrive at 11:15am for set-up. | P
Full COLD Meeting Room | LIB 2022 | Have name plates available for all attendees | P
Breakfast Space | LIB 2022 |  | P
Full COLD Meeting Room | LIB 2022 |  | P
Lunch Space | Epicure Restaurant | Originally scheduled grab and go sandwiches, rearranged to sit-down lunch with attendees who chose to stay. | P
Accommodations |  | Notes | Status
Hotel Block Reserved | Yes | Scheduled 10 rooms for ExCom, had to increase the number of rooms to 15 to account for people arriving the night before. A total of 25 rooms were requested. Note to future planners: Get an actual headcount from your dean of attendees. There may be additional attendees from the CO you are not anticipating. | P
Hotel Name | Larkspur Landing
Hotel Contact | Kim Baynard
Booking Deadline? | 2018-09-02
Food |  | Notes | Status
Ex Com Dinner Location | Zocalo | This is a non-host meal. Each attendee pays. | P
Day 1 Lunch | Epicure Catering | Order for 25 • Sandwich & Salad Combo, w/iced tea • Additional Salad • Hot coffee | P
Snacks | Costco | Purchased by A. Kautzman before event. Served half-way between mealtimes throughout event. Both days. Reimbursed by Foundation Check Request. | P
Full COLD Dinner Location | Lucca | Ordered Menu #2 for 30 people. Seated in half of the Main Patio. | P
Restaurant Contact | Glenn Stewart
Day 2 Breakfast | Epicure Catering | Order for 26 • Executive Breakfast • Small Fruit Tray • Quick Breads • Decaf • Hot Tea & Cocoa Assortment • All-day coffee refresh | P
Day 2 Lunch | Epicure Restaurant | Sit-down lunch for attendees who chose to stay after adjournment. | P
Logistics | Notes |  | Status
Email to Deans | Sent 8/13/18 by A. Kautzman. I did not have the correct permissions to send to the list myself. |  | P
Doodle Survey to Deans | Included in email. Y/N Questions include: • Attending Executive Meeting? • Attending General Meeting? Day 1 • Attending General Meeting? Day 2 • Zooming? (specify dates in comments) • All COLD Lunch Day 1? • All COLD Lunch Day 2? • All COLD Dinner • Dietary Restrictions? (please specify in comments) • Will you need a parking permit? |  | P
Wi-Fi | Coordinate with Systems to get additional log-in info in case EduRoam doesn't work for attendees. |  | P
Zoom | Coordinate with Systems to set-up Zoom meeting and webcam in the event of remote-attendees. |  | P
Room set-up | Smart Room. Conference style. Food in the back. Set-up power strips for laptops. |  | P
Note on G1: Maria Ramirez: As items are completed, mark with a "P." The font will make it a check mark.