## EX Libris notes
Notes from Ben and Ophir | Documentation
https://knowledge.exlibrisgroup.com/Primo/Product_Documentation/Go_VE/Step_4%3A_Go_Live#Going_Live_with_Primo_VE
Here are some details about the actual process of switching over to Primo VE | https://3.basecamp.com/3765443/buckets/20335333/messages/3679153761
A DNS switch will be implemented, redirecting traffic from your Classic Primo front-ends to your Primo VE views. From this point on, deeplinks, permalinks, and short permalinks will be transformed into Primo VE compatible URLs. This action is seamless and doesn't involve any downtime.
Users' eShelf favorites will be copied from Classic Primo to VE. Eshelf migration job will copy existing Favorites from PBO to VE. Records saved in PBO after this job will not appear in VE as well. – For this reason we tend to run the job after the DNS switch, which ensures that users are saving their Favorites in VE and not in Classic Primo by the time we execute the job.
Primo APIs will be routed to point at Primo VE instead of PBO.
Primo Analytics data will be migrated over to Primo VE Analytics, accessible via Alma. Anything recorded in Primo Analytics after the job will not be available in VE
Primo VE will be enabled on Alma sandboxes.
Support Chat for VE will be enabled on your Alma production.
If any of the campuses are subscribed to Leganto and/or CampusM, you will adjust them to integrate with VE instead of Classic Primo.
Primo Backoffice and Frontend will be kept alive through December 2021. Your Classic Primo should stay up to date, unless you turn off publishing and harvesting.
We're happy to offer a month of post-GoLive support on Basecamp, before handing you back to our Support teams.

## Go Live Dates
Task | Notes | Status
Each campus enters date into Google sheet for DNS switch. Ex Libris will handle it from there. You do not need to open a support case as noted in Go Live documentation. | Available dates for July: 5,6,7,11,12,13,14,19,20,21,25,26,27,28.
https://docs.google.com/spreadsheets/d/1_nmfrii3sYJ1fUq4f7KJMznOffzuK7nKZEMi9KjgVQU/edit#gid=0
Multiple campuses may select the same date

## Go Live Steps
Task | Documentation | Notes | Status
Ignore some of documentation (e.g. you don't open a support case to Go Live) | https://knowledge.exlibrisgroup.com/Primo/Product_Documentation/Go_VE/Step_4%3A_Go_Live#Redirect_Permalinks_in_Primo_to_Primo_VE | Step 4 Go Live Documentation.
Process tracking page – Make sure that all tasks leading up to going live have been completed and that there are no errors. | https://knowledge.exlibrisgroup.com/Primo/Product_Documentation/Go_VE/Step_1%3A_Enablement_Phase#Tracking_the_Self-Switch_Process
Go live readiness checklist – Run the tasks on this checklist in your Primo VE environment. | https://knowledge.exlibrisgroup.com/Primo/Product_Documentation/Go_VE/Step_4%3A_Go_Live#Readiness_Evaluation
Redirect Permalinks in Primo to Primo VE | https://knowledge.exlibrisgroup.com/Primo/Product_Documentation/020Primo_VE/Primo_VE_(English)/120Other_Configurations/Configuring_Redirection_for_Primo_VE_Deep_Links | Very Important: Use the Primo Deep-Link Re-Direct Configuration page (Configuration Menu > Discovery > Other > Primo Deep-Link Re-Direct Configuration) to map the parameters used in Primo permalinks to the corresponding

## Post Live OpenURL
Task | Documentation | Notes | Examples | Status
Update your openURL with vendors | https://knowledge.exlibrisgroup.com/Primo/Product_Documentation/020Primo_VE/Primo_VE_(English)/050Display_Configuration/015Configuring_the_Services_Page_for_Primo_VE | While redirects are in place, you will need to contact your various vendors to update your openURL that is used for electronic resources. Some vendors allow you to do this yourself in the admin portal.
https://<Primo_domain>/openurl/<Alma_institution_code>/<view_code>?
https://mylibrary.primo.exlibrisgroup.com/openurl/01MY_INST/01MY_INST:VIEW1?
Fullerton: https://csu- fullerton.primo.exlibrisgroup.com/openurl/01CALS_FUL/01CALS_FUL:01CALS_FUL?
San Jose: https://csu-sjsu.primo.exlibrisgroup.com/openurl/01CALS_SJO/01CALS_SJO:01CALS_SJO?

## Search Profile (DN)
Task | Notes | Status
As discussed in Basecamp and Slack, the DN search profile should be customized (create a local custom scope) to avoid seeing other campuses' electronic resources or Sacramento's Exploro records. | Need help? Reach out to David Walker or Brandon Dudley

## Post Live Embedded Search bo
Task | Documentation | Status
Update the code for embedded Primo search boxes on your library page according to Primo VE terminology and parameters | https://knowledge.exlibrisgroup.com/Primo/Product_Documentation/020Primo_VE/Primo_VE_(English)/030Primo_VE_User_Interface/010Primo_VE_Customization_-_Best_Practices#Creating_a_Search_Box_With_Deep_Links_to_Primo_VE

## Rapid ILL
Task | Documentation | Notes
Primo to Primo VE Migration – Rapid ILL Required Actions | https://knowledge.exlibrisgroup.com/RapidILL/Implementation_Guides/Primo_to_Primo_VE_Migration_%E2%80%93_Rapid_ILL_Required_Actions | As the move from Primo to Primo VE entails a change in the discovery system, the Link Resolver Base URL field of the electronic publishing profiles should be updated to reflect that change, as detailed below. Following the changes, a full republish to Rapid ILL must be done.

## Leganto
Task | Documentation | Notes | Status
For Leganto institutions – Link Leganto to Primo VE. You can configure the repository in which Leganto users search for citations to be Primo VE. You will need the View Code for your Primo VE view. You can restrict the searches to a specific scope or allow users to search in any scope. The relevant Leganto configuration guide can be found at | https://knowledge.exlibrisgroup.com/Leganto/Product_Documentation/Leganto_Online_Help_(English)/Leganto_Administration_Guide/Configuring_Leganto_UI_Elements/03_Configuring_the_Repository_Search_in_Leganto

## Analytics
Task | Documentation | Notes | Status
Once you receive the switch-over notification, perform the following tasks: Test Primo VE Analytics and verify that Primo Analytics data is available. | https://knowledge.exlibrisgroup.com/Primo/Product_Documentation/Go_VE/Step_4%3A_Go_Live#Initiating_the_Go_Live_Process | Basecamp confirmed that we should see Primo Analytics

## Scheduled jobs
Task | Status
If you created profiles for external resources, you will need to schedule the jobs

## Rollout to Library and campus
Task | Notes | Status
Consider a communications plan to announce Primo VE to stakeholders
Inform Library once you have a Go Live Date-- | Share positive features such as Real-time discovery of records created in Alma and Enhanced Journal Search with features not available in Primo. An internal LibGuide may be helpful
Have a plan for library to report problems or ask questions | e.g, SJSU created a Google docs for 2017 Primo migration to document questions, problems, follow up
Consider sharing known issues with library | e.g. Include disappearing facets and expected resolution. Create a Google doc or internal LibGuide or point to ULMS wiki page
Let library know redirects in place but good idea to update LibGuides,etc
Update local documentation such as Primo How to Guides
Review library website | Deeplinks will take care of some of this.
Should librarians email their departments about Primo VE URL | Craft an email that librarians can send to their departments with the new Primo VE URL and permalinks (e.g., update syllabi)
Notify campus webmaster to update any links? | Update URL for OneSearch