## 01CSU
Phase |  | Activity | Months
|  |  | 2015-10-15 | 2015-11-15 | 2015-11-15 | 2015-12-15 | 2016-01-15 | 2016-02-16 | 2016-03-17 | 2016-04-18 | 2016-05-19 | 2016-06-20 | 2016-07-21 | 2016-08-22 | 2016-09-23 | 2016-10-24 | 2016-11-25 | 2016-12-26 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01
Planning |  | Kickoff meeting (onsite)
Project plan
Project status calls
Access to Sandbox
Alma training (web-based)
Provide vanguard institutions and network zone configuration and migration inputs
Vanguard institutions & network zone test load and configuration
Primo initial configuration & delivery
Workflow and data review
Implementation | Define | Kickoff meeting with analysis (onsite)
Access to Sandbox
Alma training (web-based)
Monitor Go Live readiness
Provide configuration & migration inputs
| Build | Test load and configuration
3rd party integrations incl. authentication
Access to Alma Production and Primo environment
Workflow and data review
Monitor Go Live readiness
Workshop 1 (onsite)
Resource Sharing Configuration
Certification training (web-based)
Workshop 2 (onsite)
Library staff training
Cutover
| Deploy | Go Live
Relink San Marcos and Sacracmento to network zone
Alma health check
Switch to Support