## All Other Tabs
Tab | Who is Responsible for Completing this Tab? | What Consortial Decisions are Required? | Date the Tab Info is Due Internally | To Whom is the Tab Data Initially Submitted? | Date the Tab Info is Due to Ex Libris
Questionnaire | See "Questionairre Tab" Worksheet |  | 2014-07-03 | Mitch and Paula | 2014-07-23
Alma Libraries | Campus per recommendations from Discovery Team | Naming standards | 2014-07-14 | Mitch and Paula | 2014-07-23
Location Mapping | Campus per recommendations from Discovery Team | Naming standards | 2014-07-14 | Mitch and Paula | 2014-07-23
Reporting Codes | Campus per recommendations from Acquisitions Team | Naming standards | 2014-07-14 | Mitch and Paula | 2014-07-23
PO Line Types | Campus per recommendations from Acquisitions Team | ? | 2014-07-14 | Mitch and Paula | 2014-07-23
Fiscal Periods | Campus | None | 2014-07-14 | Mitch and Paula | 2014-07-23

## Questionairre Tab
Who is responsible for completing this line
Last Updated: Mar 23 2014
| GENERAL | FILL IN THIS COLUMN | INSTRUCTIONS | INTERNAL CODE | NOTES TO EXL, IF NECESSARY
Pre-populated | Institution Code (as determined by the Alma Migration Team) | 01UWI_ML |  | INST_CODE
Pre-populated | Customer Code (as determined by the Alma Migration Team) | 01UWI |  | CUST_CODE
Pre-populated | Institution Name | University of Wisconsin - Milwaukee |  | INST_NAME
Pre-populated | Institution Id (as determined by the Alma Migration Team) | 2124 | Institution ID in Alma. This is MANDATORY to be filled in by Ex Libris. | INST_ID
Pre-populated | Customer Name | University of Wisconsin |  | CUST_NAME
Pre-populated | Voyager DB name to migrate | milwaukeedb | e.g. myuniversitydb. Limit to one DB name. | VOYAGER_DB
Pre-populated | Time Zone | US/Central | Mandatory | TIMEZONE
Campus (Please highlight if not using default) | Limit data exported by location: Unless instructed otherwise by your Ex Libris project manager, leave this as No. | No | Possible Values: No (default)=migrate all data in the listed db Yes=migrate data from the list of locations on the location tab onlyValue from LIBRARY.LIBRARY_NAME=migrate only data for the listed owning library | OWNING_LIBRARY_OR_LOCATIONS | Wisconsin campuses will use default unless instructed otherwise
INVENTORY
Campus (Please highlight if not using default) | Migrate SFX records? (Y/N) | No | Yes = Bibs in Voyager which were loaded from SFX will be included in Alma No = Bibs in local ILS which were loaded from SFX will be excluded from Alma, presumably because we are also extracting the same records from SFX. (default) | MIGRATE_SFX | Wisconsin campuses will use default unless instructed otherwise
Eresource Functional Team | Migrate E-Items? (Y/N) | No | Yes = generate regular Alma items for E-items in Voyager No = do not migrate E-items from Voyager (default) | MIGRATE_EITEMS
Resource Management Team | Migrate Suppressed Serial Issues? (Y/N) | No | Yes = Serial issues marked as OPAC suppressed in Voyager will be migrated to Alma with a note indicating that they were suppressed in Voyager. No = do not migrate suppressed serial issues (default) | MIGRATE_SUPP_SERIAL_ISS
Resource Management Team | MARC Organizational Code |  | Example: NjP. Mandatory. Used to build a prefix for the former Voyager system number in a 035 ¦a field. | MARC_OC
Resource Management Team | Include "-Voyager" in 035 | No |  | INCLUDE_035_SUFFIX
Resource Management Team | Bib tag (9xx) for owning library information |  |  | TAG_FOR_OWNING_LIB
Resource Management Team | Move 852$c to another subfield | k | $c will be used by Alma; if you have anything in $c, we will move to the subfield specified | MOVE_852C_SUBF
Resource Management Team | Do you use internal system numbers in $w of Linked Entry fields? | No | Tell us if you use the local system number in $w of 76x-78x linking fields.(Yes/No) Default = No | LINKED_ENTRY_W
Resource Management Team | Internal record designation for Linked Entry fields $w |  | If Yes for the previous question and the internal system numbers have a prefix, enter the value that we will match on to identify the local system number If no prefix, then leave blank | LINKED_ENTRY_PREFIX
COURSES
Resource Management Team | Bib tag and text which will contain a Course indication |  | Specify a bib tag and subfield plus text which will include text that will indicate a bib is attached to a course (ex: '960 $a ON RESERVE') | TAG_FOR_COURSE_RES
PATRONS
Tech/Data Team | Which identification number should be used by externally managed patrons to identify themselves and login to Primo as the user's Primary Identifier? | Institution ID | Institution ID or most recent active barcode. Externally managed users are created and managed by an external system. | PATRON_USERNAME_EXT
Tech/Data Team | Which identification number should be used by internally managed patrons to identify themselves and login to Primo as the user's Primary Identifier? | Institution ID | Institution ID or most recent active barcode. Internally managed users are created and managed solely by the library, for example community borrowers. | PATRON_USERNAME_INT
Tech/Data Team | Augment Externally managed users' identification number? | None | Indicate if you wish to add a prefix or suffix to the identification number of an externally managed user. Valid responses: Prefix, Suffix, None | AUGMENT_USERNAME_EXT
Tech/Data Team | If Prefix or Suffix to the above question, list value here |  | List prefix or suffix here | AUGMENT_EXT_VALUE
Tech/Data Team | Augment Internally managed users' identification number? | None | Indicate if you wish to add a prefix or suffix to the identification number of an internally managed user. Valid responses: Prefix, Suffix, None | AUGMENT_USERNAME_INT
Tech/Data Team | If Prefix or Suffix to the above question, list value here |  | List prefix or suffix here | AUGMENT_INT_VALUE
Tech/Data Team | Enter a two letter code for the default conversational language for your users (for example en or fr) | en |  | PATRON_LANG
| How many years of old fines should we migrate? | 0 (only current fines) |  | FINE_HISTORY
Tech/Data Team | Patron Group code(s) which will migrate as Internal in Alma |  | Indicate the patron group codes which will not be managed in an external system feed - separated by comma: e.g. STAFF, WALKIN, ALUMNI | PATRON_INTERNAL
ACQUISITIONS
Acquisitions | Has your library contracted with Ex Libris to migrate Acquisitions data? | Full | Mandatory Full = Full Acquisitions None = No Acquisitions Partial = Vendors, Funds, Purchase Orders (no Invoices) | ACQ_MODE
Acquisitions | Close purchase orders that are NEW and older than x years | 0 (do not move any to closed) |  | PO_NEW_HISTORY
Acquisitions | Close purchase orders that are SENT and older than x years | 0 (do not move any to closed) |  | PO_SENT_HISTORY
Acquisitions | Close purchase order that are single part (0), have been invoiced, and are older than x years | 0 (do not move any to closed) |  | PO_INV_HISTORY
Acquisitions | Central Ordering Library |  | You may choose to override the ORDER_LOCATION for purchase orders and designate a central ordering library for ALL purchase orders. If so, enter a valid Alma Library code here. If not, fill in the following Default Order Library question. | CENTRAL_ORDER_LIB
Acquisitions | Default Order Library |  | If you do not specify a Central Ordering Library, then specify a Default Order Library to use if ORDER_LOCATION is blank. | DEFAULT_ORDER_LIB
| Modify the default PO Line Type Mapping? |  | If Yes, then use map in "PO Line Types" tab | MAP_REPCODE_LINE_TYPE
Acquisitions | Renewal date |  | Enter the renewal date for all your active subscriptions (YYYYMMDD) | RENEWAL_DATE
FUNDS
Acquisitions | Fiscal Period Cycle Pattern (DD-MM-C) | 01-07-1 | Ex: 01-07-1 for FP beginning 1 July (01-07), for 1 year (C). Mandatory. | FISCAL_PERIOD
Acquisitions | Manually map fiscal periods from Voyager to Alma | Yes | If Yes, then use the Fiscal Period Map tab | USE_FP_MAP
Acquisitions | Map Reporting Codes (Y/N) | No | If yes, then use map in "Reporting Codes" tab | MAP_REPCODE
Acquisitions | Convert Reporting Funds to Allocated Funds? | No | If mapping reporting codes = Y, then this cannot also be Y. | REPCODE_TO_ALLOC
P2E
Eresource Functional Team and Resource Management | Which Holding or Bib field stores electronic link information | 856 u | Provider 3 digit Marc field code + 2 optional indicators + subfield default: 856 u | P2E_LINK
Eresource Functional Team and Resource Management | Which Holding or Bib field stores electronic link public note | 856 z | Provider 3 digit Marc field code + 2 optional indicators + subfield default: 856 z | P2E_NOTE
Eresource Functional Team and Resource Management | Which Holding or Bib field stores electronic provider name information | 856 m | Provider 3 digit Marc field code + 2 optional indicators + subfield | P2E_PROVIDER