## Group 1
Group 1: Maritime, East Bay, Humboldt (Voy), Chico, Bakersfield (Voy), Dominguez Hills, Northridge, Fresno
Week Of | Activities | Downtime
2017-04-02 | CSU updates Alma Health Checklist on Basecamp; CSU begins prep of Migration Form, Field Mapping Form (III), P2E, 360 Forms, Delivered Files List; ExL Project Team answers questions and assists with checklist issues | n/a
2017-04-09 | CSU continues prep of Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List; ExL sending feedback & answering questions from forms and health checklist | n/a
2017-04-16 | DRAFT Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List posted to SF case for ExL Project & Migration Teams review | n/a
2017-04-23 | Final revisions to Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List updated to SF case; ExL sending feedback & answering questions
2017-04-30 | FINAL Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List due via SF cases for Migration Team Review
2017-05-07 | Data files due on ExL FTP server by end of week | III + Voy tech freeze (no further Cat + Acq); Alma config freeze begins
2017-05-14 | Migration activities
2017-05-21 | Migration activities
2017-05-28 | ExL Project Team checks migrated data
2017-06-04 | ExL Project Team delivers cutover environment; campuses + CO check data; data publishing to Primo is started; CSU confirms acceptance of Alma data migration; CSU delivers final fulfillment data (loans, patrons, requests) | Primo config freeze begins; Alma config freeze ends
2017-06-11 | Primo publishing completes; ExL Migration loads fulfillment data; ExL Project Team checks and delivers Alma & Primo to CSU; CSU checks fulfillment data & Primo and confirms acceptance; ExL turns on job schedule and unscrubs e-mail; GO LIVE DATE IS 6/13 -- each campus notifies CSU and ExL when live work has begun | III + Voy circ freeze (no further activity in III, Voy, or 360; use Alma Offline Circ - 2 days); Primo config freeze ends
2017-06-18 | CSU updates Alma Health Checklist; ExL Project Team answers questions and assists with checklist issues
2017-06-25 | Planning for Switch To Support (est 7/31)

## Group 2
Group 2: Monterey Bay (Voy), Sonoma, Fullerton, Channel Islands (Voy), Los Angeles, Long Beach, Pomona
Week Of | Activities | Downtime
2017-04-09 | CSU updates Alma Health Checklist on Basecamp; CSU begins prep of Migration Form, Field Mapping Form (III), P2E, 360 Forms, Delivered Files List; ExL Project Team answers questions and assists with checklist issues | n/a
2017-04-16 | CSU continues prep of Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List; ExL sending feedback & answering questions from forms and health checklist | n/a
2017-04-23 | DRAFT Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List posted to SF case for ExL Project & Migration Teams review | n/a
2017-04-30 | Final revisions to Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List updated to SF case; ExL sending feedback & answering questions
2017-05-07 | FINAL Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List due via SF cases for Migration Team Review
2017-05-14 | Data files due on ExL FTP server by end of week | III + Voy tech freeze (no further Cat + Acq); Alma config freeze begins
2017-05-21 | Migration activities
2017-05-28 | Migration activities
2017-06-04 | ExL Project Team checks migrated data
2017-06-11 | ExL Project Team delivers cutover environment; campuses + CO check data; data publishing to Primo is started; CSU confirms acceptance of Alma data migration; CSU delivers final fulfillment data (loans, patrons, requests) | Primo config freeze begins; Alma config freeze ends
2017-06-18 | Primo publishing completes; ExL Migration loads fulfillment data; ExL Project Team checks and delivers Alma & Primo to CSU; CSU checks fulfillment data & Primo and confirms acceptance; ExL turns on job schedule and unscrubs e-mail; GO LIVE DATE IS 6/20 -- each campus notifies CSU and ExL when live work has begun | III + Voy circ freeze (no further activity in III, Voy, or 360; use Alma Offline Circ - 2 days); Primo config freeze ends
2017-06-25 | CSU updates Alma Health Checklist; ExL Project Team answers questions and assists with checklist issues
2017-07-02 | Planning for Switch To Support (est 7/31)

## Group 3
Group 3: San Jose, Stanislaus, San Bernardino, San Luis Obispo, Moss Landing, San Diego, San Francisco
Week Of | Activities | Downtime
2017-04-16 | CSU updates Alma Health Checklist on Basecamp; CSU begins prep of Migration Form, Field Mapping Form (III), P2E, 360 Forms, Delivered Files List; ExL Project Team answers questions and assists with checklist issues | n/a
2017-04-23 | CSU continues prep of Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List; ExL sending feedback & answering questions from forms and health checklist | n/a
2017-04-30 | DRAFT Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List posted to SF case for ExL Project & Migration Teams review | n/a
2017-05-07 | Final revisions to Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List updated to SF case; ExL sending feedback & answering questions
2017-05-14 | FINAL Migration Form, Field Mapping Form, P2E, 360 Forms, Delivered Files List due via SF cases for Migration Team Review
2017-05-21 | Data files due on ExL FTP server by end of week | III + Voy tech freeze (no further Cat + Acq); Alma config freeze begins
2017-05-28 | Migration activities
2017-06-04 | Migration activities
2017-06-11 | ExL Project Team checks migrated data
2017-06-18 | ExL Project Team delivers cutover environment; campuses + CO check data; data publishing to Primo is started; CSU confirms acceptance of Alma data migration; CSU delivers final fulfillment data (loans, patrons, requests) | Primo config freeze begins; Alma config freeze ends
2017-06-25 | Primo publishing completes; ExL Migration loads fulfillment data; ExL Project Team checks and delivers Alma & Primo to CSU; CSU checks fulfillment data & Primo and confirms acceptance; ExL turns on job schedule and unscrubs e-mail; GO LIVE DATE IS 6/27 -- each campus notifies CSU and ExL when live work has begun | III + Voy circ freeze (no further activity in III, Voy, or 360; use Alma Offline Circ - 2 days); Primo config freeze ends
2017-07-02 | CSU updates Alma Health Checklist; ExL Project Team answers questions and assists with checklist issues
2017-07-09 | Planning for Switch To Support (est 7/31)