## Slide 1: Go VE – Consortia Self Switch CSU -Early Access
Jan 2021

## Slide 2
Self-Switch Process for Consortium
Getting Started for an institution level
Authentication
Documentation
Timeline
Self Configuration Tasks
Communication

## Slide 3: Self-Switch Process for Consortium
Enablement
  Consortium (NZ)
  Start the process
  Create unified index
  Copy Central package
Authentication
  Institution only (IZ)
  Configure User Authentication
Configuration
  Consortium (NZ)
  Plan the central management
  Configure the central configuration
Go Live!
  DNS switch
  Redirection to primo VE
  Live enablement
  Copy Favorites and Analytics
  Institution (IZ)
  Create views from Primo
  Copy Customization and translations from Primo
  Copy PC key from Primo
  Institution (IZ)
  Configure the features in institution level (consortia related and other features)
Notes: Documentation – getting started

## Slide 4: Getting Started for an institution level
Enablement for consortium documentation

## Slide 5: Authentication
Authentication documentation
Setup in parallel to Configuration Phase
May require involvement of institutional IT department

## Slide 6: Documentation
Consortia related features documents:
  Getting Started with Collaborative Networks
  Converting Collaborative Network Features to Primo VE
Go VE documentation
Primo VE documentation

## Slide 7: Timeline
Bi-weekly topics and tasks
Bi-weekly meetings during Jan-April
  Feedback on previous topic self configuration
  Technical Q&A
  Assignments for coming week
Goals for April 2021;
  Enablement completed
  Authentication completed
  Configuration in progress

## Slide 8: Self Configuration Tasks
Institution Level configuration
Enablement of the institutions (By Jan 19th)
Configuring authentication (By Feb 16th)
Configuring a view (By Feb 2nd)
Configuring search scope + profile + slot (By Feb 16th)
Configuring Display field & local field (By March 2nd)
Adding a local resource type (By March 2nd)
Setting up an external DS import profile (By March 16th)
Consortium level configuration (By Feb 2nd)
Analyzing central management configuration in Primo
Planning the setup in NZ and IZ levels
The areas are: local fields, default display fields and local resource types

## Slide 9: Communication
Basecamp - technical questions
Bi - Weekly meetings – self-switch feedback
Conclusion meeting – April 6th
April 6th – Go Live( End of May);
  Basecamp discussions
  Go_VE@exlibrisgroup.com
  Periodic meetings – if needed

## Slide 10
Thank you!